## Summary
Project Name: |  | Tomcat Take Out
Team Member: |  | CD | Dev | Elvis | UI Dev
|  | Nick | Dev | Suky | BA Dev
|  | Ace | Dev
|  | Joey | Dev
Module: |  | TTO_Admin
TTO_Client
TTO_Vendor
GitHub: | https://github.com/ITA-2015-G01-O2O/G01_Project.git

## Schedule
Item\Time | 8/22/2015 | 8/23/2015 | 8/24/2015 | 8/25/2015 | 8/26/2015 | 8/27/2015 | 8/28/2015
Confirm Requirement | *
Business Flow | *
UI Design | * | *
Framework Build | * | *
Common Build | * | *
Normal Dev |  | * | * | * | * | *
QA | [5 empty] | * | *

## Resources Plane
Module | Item | Sub-Item | Resources | effort point | Remarks
TTO_Admin | User_Manage | User_Search | CD |  | Extjs4.2
|  | User_View | CD
|  | User_Update | CD
| Vendor_Manage | Vendor_Search | CD
|  | Vendor_View | CD
|  | Vendor_Update | CD
| Config_Manage | Cosntant_Config | CD
|  | Mutil_Value_Config | CD
| Support_Function | Login | CD
TTO_Client | Location | Location | Nick/Elvis/Joey |  | Bootstrap3
| Register | Register | Nick/Elvis/Joey
| Home_Page | Hot_Vendor | Nick/Elvis/Joey
|  | Vendor_Search | Nick/Elvis/Joey
| Product | Product_Search | Nick/Elvis/Joey
|  | Cart | Nick/Elvis/Joey
| Order | Order_Create | Nick/Elvis/Joey
|  | Order_Search | Nick/Elvis/Joey
|  | Order_Update | Nick/Elvis/Joey
| User_Profile | User_Profile_View | Nick/Elvis/Joey
|  | User_Profile_Update | Nick/Elvis/Joey
|  | Fund_Manager | Nick/Elvis/Joey
| Support_Function | Login | Nick/Elvis/Joey
|  | Customer-Service | Nick/Elvis/Joey
TTO_Vendor | Register | Register | Ace/Suky |  | Bootstrap3
| Product | Product_Search | Ace/Suky
|  | Product_Create | Ace/Suky
|  | Product_View | Ace/Suky
|  | Product_Update | Ace/Suky
|  | Product_Delete | Ace/Suky
| Product Label | Product_Label_Create | Ace/Suky
|  | Product_Label_View | Ace/Suky
|  | Product_Label_Search | Ace/Suky
|  | Product_Label_Delete | Ace/Suky
| Order | Order_View | Ace/Suky
|  | Order_Update | Ace/Suky
| Vendor_Profile | Vendor_Profile_View | Ace/Suky
|  | Vendor_Profile_Update | Ace/Suky
| Support_Function | Customer-Service | Ace/Suky
|  | Login | Ace/Suky

## Stroy
Admin |  |  | User
| 1.管理员可以获取所需的用户信息 |  |  | 1.用户可以通过必须信息注册
| 2.管理员可以重置用户密码 |  |  | 2.用户可以获取所有的可配送地点
| 3.管理员可以获取所需的商家信息 |  |  | 3.用户可以选择当前的配送范围
| 4.管理员可以根据商家的评级信息对商家店铺进行状态更换 |  |  |  | 3.1用户可以更换配送范围
|  | 4.1 商铺平均评分、商铺订单评价、客服指数等（BA Confirm） |  | 4.用户可以获取热门商铺列表以及所需商铺
| 5.管理员可以根据商铺提供的信息进行商铺审核 |  |  |  | 4.1用户可以通过关键字获取所需商铺
|  | 5.1注册审核 |  |  | 4.2用户可以通过条件获取所需商铺
|  | 5.2更新审核 |  | 5.用户可以通过选择商铺获取相应的产品信息
| 6.管理员可以获取所需的系统配置参数 |  |  | 6.用户可以选择自己所需产品并添加至购物车
| 7.管理员可以更改所需的系统配置参数 |  |  |  | 6.1 用户可以通过标签筛选产品
7.用户可以对当前购物车进行结算操作，并获取相应的订单
8.用户可以查询自己的订单状态以及相应的产品、商铺信息
9.用户可以对未接受的订单进行取消
10.用户可以对已完成的订单进行评分、评价
Vendor |  |  |  | 11.用户可以查看更新自己的账号信息
| 1.用户可以通过申请拥有商家身份 |  |  |  | 11.1 配送地址、电话号码、姓名、账号余额（BA Confirm）
| 2.商家可以获取自己的商铺信息 |  |  | 12.用户可以充值账户
3.商家可以更换商铺Logo、商铺名称、商铺配送范围
4.商家可以为商铺管理产品标签（CRUD）
5.商家可以为商铺添加产品
6.商家可以为商铺冻结产品
7.商家可以获取新进订单
8.商家可以对订单进行状态更换
8.1 接受、配送、确认
9.商家可以获取所有的完成订单
Order

## Filed
Configuration | name | Admin | user phone | Store | store name | Store Profile | id card number
| value |  | password |  | location |  | id card picture
[5 empty] | service begin time |  | license picture
Account | username | User Profile | fund |  | service end time |  | real store picture
| password |  | email |  | deliver fee |  | store
| user profile |  |  |  | starting fee |  | status
| store | Collect | user profile |  | avg point
|  |  | store |  | avg deliver time
store logo pic
|  | Location | area
|  |  | city | Product | product name | Product Label | name
|  |  | place |  | price |  | store
sales volume
product picture
Order | user profile | order item | product |  | product label
| store |  | order |  | store
| order number |  | price
| create time |  | amount
end time
| status | Comment | order
| target name |  | time
| target location |  | context
| target phone |  | point
total price